NutriLog

Project Plan

Version 1.0  ·  March 2026  ·  Single-user personal nutrition tracker

| Project Name | NutriLog — Personal Nutrition Tracker |
| --- | --- |
| Document Type | Project Plan |
| Version | 1.0 |
| Status | DRAFT — Pending owner approval |
| Product Owner | TBD |
| Developer | Claude (Anthropic AI) |
| Start Date | TBD (upon PRD approval) |
| Target Go-Live | TBD + ~4 weeks |
| Budget | $0 direct cost (all free-tier services) |

# 1.  Project Overview

NutriLog is a personal, single-user web application for logging daily food intake and tracking nutritional progress against self-defined targets. It is built entirely on free-tier infrastructure: a static frontend hosted on GitHub Pages, a Google Apps Script backend, and a Google Spreadsheet as the data store.

## 1.1  Objectives

- Deliver a working, cross-device web application accessible on both iPhone 13 Pro and Mac.

- Provide a food logging flow that completes in under 30 seconds per entry on mobile.

- Establish a maintainable, modular codebase that supports future iteration without architectural rework.

- Produce complete project documentation (PRD, Dev Standards, API Spec, Data Schema, Deployment Runbook) alongside the working application.

## 1.2  Success Criteria

| Criterion | Measurement | Target |
| --- | --- | --- |
| Logging speed | Time from opening app to confirmed log entry on iPhone | < 30 seconds |
| Load time | Today’s log page first load on mobile network | < 2 seconds |
| Search latency | Food search result return time | < 1.5 seconds |
| Data durability | Log entries visible after clearing browser cache | 100% (data in Sheets) |
| Cross-device consistency | Same totals shown on Mac and iPhone simultaneously | 100% match |
| All test cases pass | 11 test cases in DevStandards §11 pass without errors | 11 / 11 |

# 2.  Project Document Register

The following documents are required for this project. All must be completed and owner-approved before the associated phase begins.

| Doc ID | Document Title | Status | Required Before | Owner |
| --- | --- | --- | --- | --- |
| DOC-01 | Product Requirements Document (PRD) v0.3 | DRAFT | Phase 1 development | Product Owner |
| DOC-02 | Development Standards & Conventions v1.1 | COMPLETE | Phase 1 development | Developer |
| DOC-03 | Project Plan (this document) v1.0 | DRAFT | Phase 0 approval | Product Owner |
| DOC-04 | Data Schema Document | NOT STARTED | Phase 1 — Sprint 1 | Developer |
| DOC-05 | API Specification Document | NOT STARTED | Phase 1 — Sprint 2 | Developer |
| DOC-06 | Deployment Runbook | NOT STARTED | Phase 2 — UAT | Developer |
| DOC-07 | Test Plan & UAT Sign-off | NOT STARTED | Phase 2 — UAT | Product Owner |
| DOC-08 | Changelog (ongoing) | NOT STARTED | Phase 1 start | Developer |

# 3.  Scope

## 3.1  In Scope (MVP)

- Today’s Log: add/edit/delete food entries and Meal templates, grouped by meal type (Breakfast, Lunch, Dinner, Snacks, Other).

- Quick Add: fast nutrition entry without food database lookup.

- Food Search: real-time search across NutritionDB (~2,500 items) and Custom Foods.

- Custom Foods: create, edit, delete, and favourite personal food entries.

- Meal Templates: composed and manual Meal creation, editing, deletion, and quick logging.

- Nutrition Summary: daily totals vs. targets with progress bars.

- DailySummary Sync: manual sync button to write totals to DailySummary sheet.

- History: view past daily logs by date.

- Settings: nutrition target editing and PIN management.

- Access control: PIN + session token.

- Cross-device access: iPhone Safari and Mac Safari/Chrome via single URL.

## 3.2  Out of Scope (MVP)

- Native iOS/Android app.

- Biometric-based target calculation.

- Exercise / calorie expenditure tracking.

- Third-party nutrition API integration.

- Offline write capability.

- Multi-user support.

- Barcode scanning.

- Data visualisation charts (planned v2).

# 4.  Development Schedule

The project is structured into three phases. All durations are calendar time based on a single developer working in focused sessions of 2–4 hours. Elapsed time will be longer than effort time due to owner review and approval gates.

## 4.1  Phase Summary

| Phase | Name | Duration | Key Deliverable | Gate |
| --- | --- | --- | --- | --- |
| Phase 0 | Foundation & Setup | 3–5 days | Google Sheets structure ready, GitHub repo initialised, Apps Script deployed (empty shell) | Owner confirms infrastructure ready |
| Phase 1 | Core Development | 10–14 days | Working application with all MVP features | Owner UAT sign-off |
| Phase 2 | Testing & Polish | 3–5 days | Bug-free application, all test cases passing | Owner go-live approval |
| Phase 3 | Go-Live & Handover | 1–2 days | Live URL, Deployment Runbook, project archive | Project closed |

## 4.2  Phase 0 — Foundation & Setup

▶ Prerequisite: PRD v0.3 and Project Plan approved by owner before this phase begins

| Task ID | Task | Owner | Est. Days | Dependency |
| --- | --- | --- | --- | --- |
| P0-01 | Approve PRD v0.3 and Project Plan | Product Owner | 1 | PRD v0.3 final |
| P0-02 | Create GitHub repository ‘nutrilog’; set up folder structure per DevStandards §1.1 | Product Owner | 0.5 | P0-01 |
| P0-03 | Prepare Google Spreadsheet: rename existing sheets to match schema; add Favourites sheet; upload NutritionDB CSV data | Product Owner | 1 | P0-01 |
| P0-04 | Developer generates Data Schema Document (DOC-04); owner reviews | Developer + Owner | 0.5 | P0-03 |
| P0-05 | Deploy empty Apps Script Web App shell; confirm URL is accessible; add URL to config.js | Developer | 0.5 | P0-02, P0-03 |
| P0-06 | Enable GitHub Pages on main branch; confirm index.html loads | Product Owner | 0.5 | P0-02 |

## 4.3  Phase 1 — Core Development

### Sprint 1 — Backend Foundation (Days 1–4)

| Task ID | Task | Deliverable |
| --- | --- | --- |
| S1-01 | Generate API Specification Document (DOC-05) | DOC-05 approved by owner |
| S1-02 | Implement Apps Script: auth (PIN verify, token), getSettings, updateSettings | verifyPin and settings endpoints working |
| S1-03 | Implement Apps Script: searchFoods (NutritionDB + CustomFoods) | Search returns results in < 1.5s |
| S1-04 | Implement Apps Script: getDailyLog, addLogEntry, updateLogEntry, deleteLogEntry | Log CRUD working; DailyLog sheet updating |
| S1-05 | Implement Apps Script: addQuickAdd, deleteCustomFood | Quick Add creates linked CustomFood + DailyLog entry |
| S1-06 | Implement Apps Script: getMeals, saveMeal, deleteMeal | Meal template CRUD working |
| S1-07 | Implement Apps Script: toggleFavourite, getFavourites | Favourites persisting in Sheets |
| S1-08 | Implement Apps Script: syncDailySummary | Sync writes correct totals to DailySummary sheet |
| S1-09 | Owner smoke-test all endpoints using a REST client | All endpoints return {ok:true, data:...} |

### Sprint 2 — Frontend Core (Days 5–9)

| Task ID | Task | Deliverable |
| --- | --- | --- |
| S2-01 | Build HTML structure (index.html, all section scaffolds with semantic IDs) | All screens render (empty) |
| S2-02 | Implement tokens.css and main.css (design system, responsive layout, olive/warm palette) | Mac 2-col and iPhone 1-col layouts correct |
| S2-03 | Implement auth.js: PIN screen, session token, sessionStorage | PIN flow working end-to-end |
| S2-04 | Implement store.js: state object and all setter functions | State updates trigger no errors in console |
| S2-05 | Implement api.js: all fetch wrappers with [api] logging and error handling | All API calls return data in DevTools Network tab |
| S2-06 | Implement log.js: render Today’s Log, meal sections, add-entry flow, inline amount edit | Log renders; amount edit saves to Sheets |
| S2-07 | Implement search.js: real-time food search, Quick Add flow | Search returns results; Quick Add creates entry |
| S2-08 | Implement meals.js: Meal template list, create/edit Composed and Manual Meals, add-to-log | Meals CRUD working; adding Meal creates log entry |

### Sprint 3 — Remaining Features + Polish (Days 10–14)

| Task ID | Task | Deliverable |
| --- | --- | --- |
| S3-01 | Implement library.js: Custom Foods CRUD, Favourites toggle | Custom Foods list; Favourites persist |
| S3-02 | Implement history.js: date picker, load past log by date | Past log loads correctly for any date |
| S3-03 | Implement settings.js: target editing, PIN change | New targets save; PIN change works |
| S3-04 | Implement Sync button in log.js: call syncDailySummary, show toast | DailySummary row updated on tap |
| S3-05 | Implement copy-yesterday feature in log.js | Yesterday’s entries duplicated to current date |
| S3-06 | Implement entry move (Mac drag/drop; iPhone long-press menu) | Entries move between meal sections |
| S3-07 | Implement ui.js: toast notifications, progress bars, modal scaffold | All UI feedback components working |
| S3-08 | Cross-device review: test on iPhone Safari and Mac Chrome | No layout breaks, no console errors |

## 4.4  Phase 2 — Testing & Polish

| Task ID | Task | Owner | Est. Days |
| --- | --- | --- | --- |
| T-01 to T-11 | Execute full test checklist from DevStandards §11 | Product Owner + Developer | 1–2 |
| BUG-FIX | Developer fixes all issues identified during testing | Developer | 1–2 |
| DOC-06 | Developer writes Deployment Runbook | Developer | 0.5 |
| DOC-07 | Owner completes UAT sign-off checklist | Product Owner | 0.5 |
| PERF | Verify load time < 2s and search < 1.5s on iPhone mobile network | Product Owner | 0.5 |

## 4.5  Phase 3 — Go-Live & Handover

| Task ID | Task | Owner |
| --- | --- | --- |
| GL-01 | Final git push to main; confirm GitHub Pages serves live version | Developer |
| GL-02 | Owner adds app URL to iPhone Safari home screen via ‘Add to Home Screen’ | Product Owner |
| GL-03 | Owner confirms app opens correctly on both devices | Product Owner |
| GL-04 | Developer archives all project documents in GitHub /docs folder | Developer |
| GL-05 | Project marked complete; Changelog DOC-08 updated with v1.0.0 entry | Developer |

# 5.  Milestones & Gates

Each milestone is a hard gate. The next phase does not begin until the milestone is signed off by the Product Owner in writing.

| Milestone | Description | Gate Condition | Owner Sign-off |
| --- | --- | --- | --- |
| M0 | PRD + Project Plan approved | Both documents approved in writing | Product Owner |
| M1 | Infrastructure ready | Sheets structured, GitHub Pages live, Apps Script shell deployed | Product Owner |
| M2 | Backend complete | All Apps Script endpoints passing smoke tests | Product Owner |
| M3 | Frontend complete | All screens functional on both devices; no blocking console errors | Developer |
| M4 | UAT complete | All 11 test cases pass; Deployment Runbook written | Product Owner |
| M5 | Go-live | App live on GitHub Pages; accessible from iPhone home screen | Product Owner |

# 6.  Resources

## 6.1  Team

| Role | Person | Responsibilities | Availability |
| --- | --- | --- | --- |
| Product Owner | TBD (you) | Requirements, data preparation, testing, go-live approval, ongoing content maintenance | As needed |
| Developer | Claude (Anthropic AI) | All code generation, document generation, technical decisions, debugging support | On-demand (per conversation) |

## 6.2  Infrastructure & Tools

| Resource | Service | Cost | Account Required | Notes |
| --- | --- | --- | --- | --- |
| Data storage | Google Sheets / Google Drive | Free | Google account (existing) | Single Spreadsheet; ~2,500-row NutritionDB |
| Backend API | Google Apps Script | Free | Same Google account | Execution quota: 6 min/run, 90 min/day total — well within budget for this app |
| Frontend hosting | GitHub Pages | Free | GitHub account (new or existing) | Static files; 1 GB storage limit; 100 GB/month bandwidth |
| Version control | GitHub | Free | Same GitHub account | Public or private repository |
| Development environment | Any text editor (VS Code recommended) | Free | None | No local server needed; files loaded directly by browser |
| Testing — iPhone | Safari on iPhone 13 Pro | Free | None | Enable Web Inspector in iOS Settings → Safari for console access |
| Testing — Mac | Safari + Chrome | Free | None | F12 for DevTools |

## 6.3  Data Assets

| Asset | Format | Size | Owner Action Required |
| --- | --- | --- | --- |
| NutritionDB food data | CSV / Excel (existing) | ~2,500 rows | Upload to NutritionDB sheet; verify column mapping against DOC-04 |
| Custom Foods sample data | Google Sheets (existing) | 2 rows | Can be deleted (sample data) |
| DailySummary sample data | Google Sheets (existing) | 7 rows | Retain (human reference records) |

# 7.  Budget

Total direct cost: $0.00 · All services used are free-tier with no credit card required

| Item | Service | Monthly Cost | Annual Cost | Limit / Notes |
| --- | --- | --- | --- | --- |
| Data storage | Google Drive | $0 | $0 | 15 GB free; this project uses < 10 MB |
| Backend compute | Google Apps Script | $0 | $0 | 6 min/execution, 90 min/day quota; ample for personal use |
| Frontend hosting | GitHub Pages | $0 | $0 | 100 GB/month bandwidth; 1 GB repo size |
| Domain (optional) | Custom domain via GitHub Pages | $10–15/yr if desired | $10–15 | Default URL: username.github.io/nutrilog (free) |
| Developer time | Claude (Anthropic AI) | Claude.ai subscription cost | Varies | No additional cost if already subscribed |
| TOTAL |  | $0 (or $10–15/yr for custom domain) |  |  |

Note: If the app grows to require more Apps Script execution time (unlikely for personal use), Google Workspace Individual at $9.99/month provides 6-hour execution limits. This upgrade is not expected to be needed.

# 8.  Technology Stack

## 8.1  Stack Summary

| Layer | Technology | Version / Standard | Rationale |
| --- | --- | --- | --- |
| Frontend language | HTML5 + JavaScript | ES2020+ | No framework needed; native modules sufficient for this scope |
| Frontend architecture | Multi-file ES Modules (Scheme B) | ES modules (native browser) | Modular without build tools; directly deployable |
| Styling | CSS3 with custom properties | Modern CSS | Design tokens in tokens.css; BEM class naming |
| Backend language | Google Apps Script | V8 runtime | Free, serverless, native Sheets API access |
| Data store | Google Sheets | Google Sheets API v4 | Human-readable, free, no database setup required |
| Hosting | GitHub Pages | Static site | Free HTTPS, global CDN, git-based deployment |
| Authentication | SHA-256 PIN + session token | Web Crypto API | No external auth service; sufficient for single-user personal app |
| Version control | Git + GitHub | Git 2.x | Standard; required for GitHub Pages deployment |

## 8.2  Browser Compatibility Requirements

| Browser | Minimum Version | Why This Version | Features Required |
| --- | --- | --- | --- |
| Safari (iPhone) | iOS 16.4+ | ES modules and fetch() support | ES modules, fetch, sessionStorage, Web Crypto, CSS custom properties |
| Safari (Mac) | macOS Ventura (Safari 16.4+) | Same as iOS | Same as above |
| Chrome (Mac) | Chrome 90+ | Long-term stable baseline | All required features available since Chrome 61; 90+ gives ample margin |
| Firefox | Not a primary target | Not tested; should work but not guaranteed | N/A |
| Edge | Not a primary target | Not tested | N/A |

Note: The app does NOT use any polyfills, transpilation (Babel), or compatibility shims. It requires modern browser support. iPhone 13 Pro ships with iOS 15; the user must be on iOS 16.4+ for full ES module support via GitHub Pages (HTTPS required for modules).

## 8.3  Technical Constraints

- Apps Script execution quota: 6 minutes per run, 90 minutes per day for free accounts. Each user interaction triggers one Apps Script call lasting < 1 second. With up to 5 sessions/day of ~10 actions each, total daily execution is ~50 seconds. Well within quota.

- Apps Script cold start: first request after inactivity may take 3–5 seconds. Subsequent requests in the same session are fast (< 1s). The PIN verification step at session start naturally absorbs this cold-start delay.

- NutritionDB client-side cache: ~2,500 rows loaded once per session. Estimated JSON size: ~500 KB. Acceptable for modern devices; no pagination needed.

- GitHub Pages cache: static assets are cached by CDN. After a git push, changes propagate in 1–10 minutes. Not suitable for real-time configuration changes — config.js must be updated locally and pushed.

- Google Sheets rate limit: 300 requests per minute per project. Each user action triggers 1–2 Sheets API calls. At 5 sessions/day, rate limits will never be approached.

# 9.  Risk Register

| Risk ID | Risk Description | Likelihood | Impact | Severity | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R-01 | Apps Script cold start causes perceived slowness on first load | High | Low | Medium | PIN entry step absorbs cold-start delay; show loading indicator; document expected behaviour in Runbook |
| R-02 | NutritionDB CSV column names do not match expected schema | Medium | High | High | Generate Data Schema Document (DOC-04) before upload; validate first 5 rows before full import |
| R-03 | Apps Script URL accidentally committed to GitHub (secret exposure) | Low | High | High | config.js in .gitignore; config.example.js committed instead; owner instructed never to paste URL in git |
| R-04 | Google Sheets row limit reached (10M cells per spreadsheet) | Very Low | High | Low | Current design uses < 50,000 rows/year. Negligible risk for personal use. |
| R-05 | iOS Safari blocks ES modules on HTTP (not HTTPS) | Low | High | Medium | GitHub Pages always serves HTTPS. Risk only exists if testing on local HTTP server. Documented in Runbook. |
| R-06 | Apps Script deployment URL changes after redeployment | Medium | Medium | Medium | Always use a versioned deployment URL (…/exec), not a test URL. Document process in Runbook. |
| R-07 | Owner accidentally modifies NutritionDB sheet | Low | Medium | Low | Add sheet-level protection in Google Sheets (View only for NutritionDB). Document in Runbook. |
| R-08 | Future iteration breaks existing functionality | Medium | Medium | Medium | Feature branches; test checklist run before every merge to main; Changelog maintained. |
| R-09 | Session token stored in sessionStorage lost on accidental tab close | High | Low | Low | Accepted behaviour by design. User re-enters PIN (< 10 seconds). Documented as expected. |
| R-10 | Apps Script free quota exceeded during a heavy day | Very Low | Medium | Low | Monitor via Google Cloud Console. Upgrade to Workspace Individual ($9.99/mo) if needed. |

# 10.  Quality & Acceptance Criteria

## 10.1  Definition of Done (per feature)

- Feature implements all requirements stated in PRD v0.3 for that screen/function.

- No console.error() output during normal operation.

- Corresponding test case(s) from DevStandards §11 pass.

- Code follows all rules in DevStandards v1.1 (function ≤100 lines, semantic IDs, CONFIG-driven, try-catch).

- Changes committed with a correct commit message format.

## 10.2  Definition of Done (project)

- All 11 test cases from DevStandards §11 pass on both iPhone and Mac.

- All 6 documents in the Document Register are complete and owner-approved.

- App accessible via live GitHub Pages URL on iPhone and Mac without setup.

- DailySummary sheet correctly reflects data after Sync button is used.

- Owner signs UAT sign-off in DOC-07.

## 10.3  UAT Acceptance Criteria (owner-verified)

| # | Acceptance Test | Pass Condition |
| --- | --- | --- |
| AC-01 | Log a full day (3 meals + snack) on iPhone | All entries appear; totals match expected values; DailyLog rows in Sheets |
| AC-02 | Edit the amount of a logged entry | Nutrition values update correctly; Sheets row updates |
| AC-03 | Delete a Quick Add entry | Both DailyLog and CustomFoods rows deleted |
| AC-04 | Create a Composed Meal and log it | Meal appears in Meals list; logging it creates DailyLog entry with correct nutrition |
| AC-05 | Search for a food, favourite it, search again | Favourited item appears at top of results |
| AC-06 | Tap Sync and open DailySummary in Google Sheets | Row for today shows correct totals and targets |
| AC-07 | Navigate to a past date and view the log | Historical entries load correctly |
| AC-08 | Change a nutrition target and check the progress bar | Progress bar reflects new target immediately |
| AC-09 | Clear browser cache on iPhone, reopen app | PIN screen appears; after PIN entry, data reloads from Sheets |
| AC-10 | Open app on Mac simultaneously with iPhone | Both show the same data; adding entry on one device is visible on the other after reload |

# 11.  Post-Launch Iteration Framework

NutriLog is designed for ongoing iteration. The following framework governs how new features are added after the initial launch.

## 11.1  Iteration Process

- Step 1: Owner raises a new requirement (feature request or bug) via conversation with Developer.

- Step 2: Developer assesses scope: small change (< 2 hours) proceeds directly; large change requires a mini-PRD addendum.

- Step 3: Developer creates a feature branch (feature/<name>) and implements the change.

- Step 4: Owner tests the change using the relevant AC from the test checklist.

- Step 5: On approval, Developer merges to main and updates Changelog (DOC-08).

## 11.2  Planned v2 Features (in priority order)

| Priority | Feature | Estimated Complexity |
| --- | --- | --- |
| 1 | Nutrition target calculator (from height, weight, age, activity) | Medium — formula + new Settings UI |
| 2 | Weekly / monthly trend charts | Medium — Chart.js + new History view |
| 3 | Food category browsing | Low — filter on existing NutritionDB CATEGORY field |
| 4 | Sodium and potassium in daily summary | Low — data already stored; UI addition only |
| 5 | Body weight log | Low — new sheet + simple entry form |
| 6 | CSV export | Low — client-side CSV generation from DailyLog |

# 12.  Project Approval & Sign-off

This project plan is considered approved when the Product Owner confirms all sections in writing. Development (Phase 0) does not begin until this document is approved.

| Role | Name | Confirmation | Date |
| --- | --- | --- | --- |
| Product Owner | TBD | ________________________ | __________ |
| Developer (Claude) | Claude (Anthropic AI) | Awaiting owner approval |  |

NutriLog Project Plan v1.0  ·  March 2026  ·  Confidential